## Activity Log
Student Name: Rico Chao
Full Student Number: 301310624
Group Number: 54
rsvd | last 4 digits | date | starttime | endtime | rsvd | description (not too long)
| "0624" | 2020-03-29 | 9:00pm | 10:15pm |  | Creating file structure for Final Project
| "0624" | 2020-03-29 | 10:19pm | 10:52pm |  | Helped my teammates set up Git and helped them with setting up of Quartus and ModelSim
| "0624" | 2020-03-30 | 9:00pm | 10:15pm |  | Splitting tasks between team members and starting to look into Logic Unit
| "0624" | 2020-03-30 | 10:30pm | 11:00pm |  | Finished the Logic Unit
| "0624" | 2020-03-31 | 7:59pm | 10:25pm |  | Working on Arithmetic Unit
| "0624" | 2020-04-01 | 12:20pm | 1:15pm |  | Working on Arithmetic Unit, trying to fix problems
| "0624" | 2020-04-01 | 1:30pm | 4:17pm |  | Finished Arithmetic Unit and Logic Unit
| "0624" | 2020-04-02 | 7:53pm | 10:59pm |  | Worked on synthesis and documentation, will continue with screenshotting circuits tomorrow